## Slide 1: “Funding Rural and Small County HHW Collections Where Permanent Programs Do Not Exist”
Hazardous Waste Collection Center Grant - Up to $100,000 per county, for constructing one or more safe, secure, operational hazardous waste collection centers.
Cooperative Collection Center Arrangement Grant - Up to $35,000 per grant, to reimburse 75% (with a $25,000 limit) of a smaller county's collection event. The “host county”, experienced in hazardous waste collections, is reimbursed up to $10,000 for assisting the “neighboring county” in holding its collection.

## Slide 2
3. Application Process (can operate off of the Host’s EPA ID Number)
  Interlocal Agreement
  Application to participate
  Approval
    Issuance of Grant draft
    Draft review and submission
iii. Issuance of final FDEP Grant Agreement

## Slide 6
4. Event Planning
  Schedule an event (6 months out)
    Secure possible dates with Contract Hauler
    Verify date with “Neighboring County”
    Establish site for the event
      Consider traffic flow in and out as well as on site
      Site convenience for local residents
  Advertising (Host, Neighboring, or both)

## Slide 8
c. Schedule Support Vendors
  Haz-Waste
  Used Oil, Gas, and Antifreeze
  Electronics
  Mercury Containing Devices
  Support from local jurisdiction
    Garbage dumpster (discards)
    Forklift
    Management of certain materials
    Notification of local emergency services about the event
      Hospital
      Emergency Services (Fire and Rescue)
      Law Enforcement

## Slide 9
5. Conduct Mobile Collection Event
a. Final coordination with political entity and vendors one week prior to the event
b. Arrive at the collection site on the scheduled date
c. Set up can take place the morning of or the afternoon prior
d. Haz-Waste vendor conducts safety briefing prior to opening
e. Be prepared to mitigate spills/releases; may include site shutdown
f. Traffic control is important so as to prevent careless accidents
g. Helpful to have law enforcement on hand for traffic control if event site access is directly off of a major highway

## Slide 19
6. Event Shutdown
a. Local entity responsible for interfacing with locals after closure
b. Site is cleared

## Slide 20
7. Payment Process
a. Receive invoices from various vendors and remit payment
b. Receives statistics from local jurisdiction
i. Customer count
ii. Volume of materials processed by local jurisdiction
1. Sharps
2. Batteries
3. Cylinders/Fire Extinguishers
4. Fluorescent Lamps
5. Electronics

## Slide 21
8. Reimbursement Request
a. Document all costs
b. Prepare report forms
i. Event Data Summary
ii. Event Cost Summary
        Summary of Expenditures w/ invoices
  iv. FDEP Payment Request Summary Form
c. Bill local jurisdiction for their share of cost
d. Compile grant forms and support documentation
e. Bill FDEP for the cost of the mobile collection event
f. Receive reimbursement from local government/FDEP

## Slide 27: Questions/Comments?
Okaloosa County Waste Resources
850-609-6168
jreece@myokaloosa.com
www.okaloosafl.com